## Project Overview
RPO SaaS Tool - Rudra Recruiter AI
Product Requirements & Technical Specification
Version: v1.0 ¦ Owner: Rudra Enterprise LLC ¦ Date: November 2025
Category | Details
Project Name | Rudra Recruiter AI - AI-Powered Applicant Tracking System
Target Users | Internal: RPO Admin, Hiring Manager, Candidates
MVP Scope | Internal recruiters (Rudra Enterprise) - Resume parsing, AI matching, Dashboard & Reports
Technology Stack | Frontend: React/Next.js, Backend: Python FastAPI/Node.js, Database: PostgreSQL, AI: Sentence-BERT
Deployment | AWS (ECS/EC2 + RDS), S3 for storage, CloudFront CDN
Security | JWT + RBAC, AES-256 encryption, TLS 1.3
Target Metrics | 99.5% uptime, <2s match scoring, Handle 100K+ candidates
Project Phases
MVP (Current) | Internal use - Core features: Resume parsing, AI matching, Dashboard
Phase II | External client portal, Multi-tenant, AI sourcing, Predictive analytics
Key Goals
G1 | Recruiter Productivity - Automate repetitive tasks
G2 | Match Accuracy - AI-based candidate-job scoring
G3 | Central Repository - Unified candidate and job database
G4 | Insights & Reporting - Analytics and KPIs
G5 | Scalable Foundation - Ready for external rollout

## Master Task List
# | Epic/Category | Feature/Task | Task Type | Priority | Status | Complexity | Dependencies | Details/Notes
1 | Core Pages | Home Page - Design & Development | UI, Frontend | MVP | In Progress | Medium |  | Landing page with branding, navigation, and CTAs
2 | Core Pages | Login Page - Authentication UI | UI, Frontend | MVP | Done | Low |  | JWT-based authentication with validation
3 | Core Pages | Registration Page - User Signup | UI, Frontend, Backend | MVP | Done | Medium | Login | User registration with email verification
4 | Core Pages | Candidate Dashboard | UI, Frontend | MVP | In Progress | High | Login | Dashboard showing application status, jobs, analytics
5 | Core Pages | Logout Functionality | Frontend, Backend | MVP | Done | Low | Login | Session management and secure logout
6 | Epic 1: Job Requisition | Job Description Upload & Parsing | Backend, AI/ML | MVP | Not Started | High |  | Parse job description text to extract skills, experience, education
7 | Epic 1: Job Requisition | Auto-generate Ideal Candidate Profile | AI/ML | MVP | Not Started | High | Task 6 | AI analyzes JD and creates benchmark candidate profile
8 | Epic 1: Job Requisition | Job Profile Review & Tuning UI | UI, Frontend | MVP | Not Started | Medium | Task 7 | Interface for RPO admin to review and adjust AI-generated profile
9 | Epic 1: Job Requisition | Market Data Analysis (Time-to-Fill, Salary) | AI/ML, Backend | Phase II | Not Started | High | Task 7 | Estimate hiring metrics based on market data
10 | Epic 2: Sourcing | Auto-post to Job Boards (LinkedIn, Indeed, etc.) | Backend | Phase II | Not Started | High | Task 6 | API integrations with job boards for auto-posting
11 | Epic 2: Sourcing | Resume Database Search | Backend, AI/ML | MVP | Not Started | High |  | Search internal talent pool for matching candidates
12 | Epic 2: Sourcing | Passive Candidate Discovery (LinkedIn) | AI/ML, Backend | Phase II | Not Started | Very High |  | AI-powered LinkedIn scraping and matching
13 | Epic 2: Sourcing | Branded Career Page Generator | UI, Frontend, Backend | Phase II | Not Started | Medium | Task 6 | Create unique job-specific landing pages
14 | Epic 3: Screening | Resume Parsing (PDF, DOCX) | Backend, AI/ML | MVP | Done | High |  | Extract structured data from resumes - COMPLETED
15 | Epic 3: Screening | Candidate-Job Match Score Calculation | AI/ML | MVP | In Progress | Very High | Task 14 | Semantic similarity scoring (0-100) using Sentence-BERT
16 | Epic 3: Screening | Top 10 Candidate Ranking UI | UI, Frontend | MVP | Not Started | Medium | Task 15 | Display ranked candidates per job
17 | Epic 3: Screening | Match Explanation Summary | AI/ML, Frontend | MVP | Not Started | Medium | Task 15 | Show why AI recommended candidate (skills match, experience)
18 | Epic 3: Screening | Knockout Questions Setup | UI, Frontend, Backend | Phase II | Not Started | Medium |  | Configure auto-filter questions (work auth, etc.)
19 | Epic 3: Screening | Sentiment Analysis on Applications | AI/ML | MVP | In Progress | Medium | Task 14 | Analyze candidate communication sentiment - WORKING
20 | Epic 4: Engagement | Auto-confirmation Email (Application Received) | Backend | MVP | Not Started | Low | Task 14 | Send immediate confirmation to applicants
21 | Epic 4: Engagement | Auto-rejection Email (Low Match) | Backend, AI/ML | Phase II | Not Started | Medium | Task 15 | Polite rejection for <20% match score candidates
22 | Epic 4: Engagement | AI Chatbot for Candidate Q&A | AI/ML, Frontend | Phase II | Not Started | Very High |  | 24/7 chatbot for application status and FAQs
23 | Epic 4: Engagement | Personalized Outreach Message Generator | AI/ML, Backend | Phase II | Not Started | High | Task 15 | AI-drafted messages for passive candidates
24 | Epic 5: Scheduling | Self-scheduling Portal for Candidates | UI, Frontend, Backend | Phase II | Not Started | High |  | Calendar integration for candidate self-booking
25 | Epic 5: Scheduling | Calendar Integration (Google, Outlook) | Backend | Phase II | Not Started | High | Task 24 | Sync with interviewer availability
26 | Epic 5: Scheduling | Auto Calendar Invites with Video Links | Backend | Phase II | Not Started | Medium | Task 25 | Generate and send meeting invites
27 | Epic 5: Scheduling | Interview Reminder Emails (24h, 1h) | Backend | Phase II | Not Started | Low | Task 24 | Reduce no-shows with automated reminders
28 | Epic 6: Analytics | Recruiter Dashboard - Job Status Overview | UI, Frontend | MVP | Not Started | High |  | Central view of all open jobs and pipeline stages
29 | Epic 6: Analytics | Candidate Profile View (Full History) | UI, Frontend | MVP | Not Started | Medium |  | All communication, statuses, feedback in one view
30 | Epic 6: Analytics | Hiring Manager Portal (Pipeline View) | UI, Frontend | Phase II | Not Started | Medium |  | Client-facing view of candidate pipeline
31 | Epic 6: Analytics | KPI Reports (Time-to-Fill, Source-of-Hire) | Backend, Frontend | MVP | Not Started | High |  | Generate and export recruitment metrics
32 | Epic 6: Analytics | Visual Charts (Bar, Pie, Heatmap) | UI, Frontend | MVP | Not Started | Medium | Task 31 | Graphical widgets for dashboard
33 | Epic 6: Analytics | Weekly Email Summary Reports | Backend | Phase II | Not Started | Low | Task 31 | Automated report delivery to stakeholders
34 | Infrastructure | Database Schema Design (PostgreSQL) | Backend | MVP | Not Started | High |  | Design Candidate, Job, MatchScore tables
35 | Infrastructure | Elasticsearch Integration for Search | Backend | MVP | Not Started | High | Task 34 | Semantic search indexing
36 | Infrastructure | AWS S3 / Azure Blob Storage Setup | Backend | MVP | Not Started | Medium |  | Resume file storage
37 | Infrastructure | API Development (FastAPI/Express) | Backend | MVP | Not Started | Very High | Task 34 | RESTful API endpoints for all features
38 | Infrastructure | CI/CD Pipeline (GitHub Actions, Docker) | Backend | MVP | Not Started | High |  | Automated testing and deployment
39 | Infrastructure | Monitoring & Logging (Grafana, Prometheus) | Backend | MVP | Not Started | Medium |  | System health and performance tracking
40 | Infrastructure | Security Implementation (JWT, RBAC, Encryption) | Backend | MVP | Not Started | Very High | Task 37 | Authentication, authorization, data encryption
41 | AI/ML | Sentence-BERT Model Integration | AI/ML | MVP | Not Started | Very High |  | Core semantic similarity engine
42 | AI/ML | Fine-tuning Pipeline with Recruiter Feedback | AI/ML | Phase II | Not Started | Very High | Task 41 | Improve model based on user validation
43 | AI/ML | Resume Entity Extraction (Skills, Education, etc.) | AI/ML | MVP | Not Started | High |  | NLP-based structured data extraction
44 | AI/ML | Job Description Parsing & Skill Extraction | AI/ML | MVP | Not Started | High |  | Extract requirements from JD text
45 | AI/ML | Embedding Generation & Vector Storage | AI/ML, Backend | MVP | Not Started | High | Task 41 | Store and query semantic embeddings
46 | Advanced Features | Boolean Search with Filters (AND/OR/NOT) | Frontend, Backend | MVP | Not Started | Medium | Task 35 | Advanced candidate search
47 | Advanced Features | Smart Candidate Suggestions | AI/ML, Frontend | Phase II | Not Started | Medium | Task 15 | Find similar candidates feature
48 | Advanced Features | Multi-tenant Architecture | Backend | Phase II | Not Started | Very High |  | Support for multiple client accounts
49 | Advanced Features | GDPR/EEOC Compliance Features | Backend, Frontend | Phase II | Not Started | High |  | Data privacy and compliance tools
50 | Advanced Features | Audit Trail & Activity Logging | Backend | MVP | Not Started | Medium | Task 40 | Track all system changes and actions
51 | QA & Testing | Unit Testing (Backend APIs) | Backend | MVP | Not Started | Medium |  | Automated test coverage for APIs
52 | QA & Testing | Integration Testing | Backend, Frontend | MVP | Not Started | Medium |  | End-to-end workflow testing
53 | QA & Testing | UI/UX Testing & Validation | UI | MVP | Not Started | Medium |  | User acceptance testing
54 | Documentation | API Documentation (Swagger/OpenAPI) | Backend | MVP | Not Started | Low |  | Developer documentation
55 | Documentation | User Manual & Training Materials | UI | Phase II | Not Started | Low |  | End-user guides
56 | Planning | WBS (Work Breakdown Structure) | Management | MVP | Not Started | Low |  | Detailed task decomposition
57 | Planning | Resource Management Plan | Management | MVP | Not Started | Low |  | Team allocation and capacity planning
58 | Planning | Timeline & Milestone Creation | Management | MVP | Not Started | Low |  | Project schedule with deliverable dates
59 | Planning | In-scope / Out-of-scope Definition | Management | MVP | Not Started | Low |  | Clear boundary documentation

## User Stories
# | Epic | Persona | User Story | Acceptance Criteria | Task Type | Priority
1 | Epic 1: Job Requisition | Hiring Manager | As a Hiring Manager, I want to upload a simple job description, so that the AI can analyze it and generate a detailed job requisition | - Support upload of text/PDF job descriptions - AI extracts skills, experience, education - Auto-generated candidate profile displayed | AI/ML, Backend | MVP
2 | Epic 1: Job Requisition | System | As a System, I want to parse the job description to extract key requirements, so that these become the core matching criteria | - Extract 90%+ accuracy for standard fields - Structured data stored in database | AI/ML | MVP
3 | Epic 1: Job Requisition | RPO Admin | As an RPO Admin, I want to review and tune the AI-generated profile, so that I can ensure search alignment | - UI shows all extracted fields - Can add/edit/remove skills and requirements - Changes saved immediately | UI, Frontend, Backend | MVP
4 | Epic 1: Job Requisition | System | As a System, I want to analyze job requirements against market data, so that I can provide time-to-fill estimates | - Integration with market data APIs - Display estimated time and salary range | AI/ML, Backend | Phase II
5 | Epic 2: Sourcing | System | As a System, I want to auto-post approved jobs to job boards, so that I can maximize candidate reach | - API integration with LinkedIn, Indeed, Monster - Successful posting confirmation - Error handling for failed posts | Backend | Phase II
6 | Epic 2: Sourcing | System | As a System, I want to search resume databases for matching candidates, so that I can find qualified talent proactively | - Search internal database - Return relevance-ranked results - <3 second response time | Backend, AI/ML | MVP
7 | Epic 2: Sourcing | RPO Admin | As an RPO Admin, I want the AI to discover passive candidates on LinkedIn, so that I can expand my talent pool | - LinkedIn integration for profile search - Match score calculation - Suggest outreach candidates | AI/ML, Backend | Phase II
8 | Epic 2: Sourcing | System | As a System, I want to create a branded career page for each job, so that candidates have a central place to apply | - Auto-generate unique URL per job - Customizable branding - Mobile-responsive | UI, Frontend, Backend | Phase II
9 | Epic 3: Screening | System | As a System, I want to automatically parse all incoming resumes, so that I can extract structured data | - Support PDF, DOCX formats - Extract name, skills, experience, education - 95%+ parsing accuracy | Backend, AI/ML | MVP - DONE
10 | Epic 3: Screening | System | As a System, I want to give every candidate a Match Score, so that I can rank candidates by relevance | - Calculate 0-100 score using semantic similarity - Store scores in database - Update scores when job changes | AI/ML | MVP
11 | Epic 3: Screening | RPO Admin | As an RPO Admin, I want to see a Top 10 list for each job, so that I can focus on best candidates | - Display ranked list with scores - Show key match factors - Quick profile access | UI, Frontend | MVP
12 | Epic 3: Screening | Hiring Manager | As a Hiring Manager, I want to see why AI recommended a candidate, so that I can trust the system | - Display match breakdown (skills, experience) - Show matched vs missing requirements - Clear, concise summary | AI/ML, Frontend | MVP
13 | Epic 3: Screening | RPO Admin | As an RPO Admin, I want to set up knockout questions, so that the system auto-filters non-qualified candidates | - Configurable question builder - Auto-rejection based on answers - Notification to candidates | UI, Frontend, Backend | Phase II
14 | Epic 4: Engagement | Candidate | As a Candidate, I want to receive immediate confirmation after applying, so that I know my application was received | - Auto-email sent within 1 minute - Personalized with candidate name and job title - Branded template | Backend | MVP
15 | Epic 4: Engagement | System | As a System, I want to send automated rejection emails to low-match candidates, so that we maintain good employer brand | - Trigger for <20% match score - Polite, professional messaging - Configurable threshold | Backend, AI/ML | Phase II
16 | Epic 4: Engagement | Candidate | As a Candidate, I want to interact with an AI chatbot 24/7, so that I can get immediate answers | - Natural language Q&A - Answer common questions (status, requirements) - Escalate complex queries | AI/ML, Frontend | Phase II
17 | Epic 4: Engagement | RPO Admin | As an RPO Admin, I want the AI to draft outreach messages, so that I can contact passive candidates efficiently | - Generate personalized messages - Include relevant job highlights - Editable before sending | AI/ML, Backend | Phase II
18 | Epic 5: Scheduling | Candidate | As a Candidate, I want to receive a self-scheduling portal link, so that I can pick an interview time | - Email with unique scheduling link - Show available time slots - Timezone-aware | UI, Frontend, Backend | Phase II
19 | Epic 5: Scheduling | System | As a System, I want to integrate with interviewer calendars, so that I show only actual availability | - Google Calendar & Outlook sync - Real-time availability check - Handle conflicts | Backend | Phase II
20 | Epic 5: Scheduling | System | As a System, I want to auto-send calendar invites with video links, so that all parties are notified | - Generate meeting invites - Include Zoom/Teams link - Send to candidate and interviewer | Backend | Phase II
21 | Epic 5: Scheduling | System | As a System, I want to send reminder emails before interviews, so that we reduce no-shows | - 24-hour and 1-hour reminders - Include meeting details and link - Configurable timing | Backend | Phase II
22 | Epic 6: Analytics | RPO Admin | As an RPO Admin, I want a central dashboard showing all job statuses, so that I can manage my workload | - Display all open jobs - Show candidates at each stage - Filterable by date, status, client | UI, Frontend | MVP
23 | Epic 6: Analytics | RPO Admin | As an RPO Admin, I want a full Candidate Profile view, so that I see all history in one place | - Show all communication logs - Display application statuses - Include interview feedback - Timeline view | UI, Frontend | MVP
24 | Epic 6: Analytics | Hiring Manager | As a Hiring Manager, I want to see my job pipeline, so that I know status without emailing | - Simple pipeline view (Applied → Screened → Interview → Offer) - Candidate count per stage - Quick candidate preview | UI, Frontend | Phase II
25 | Epic 6: Analytics | RPO Admin | As an RPO Admin, I want to run reports on key metrics, so that I can show value to clients | - Generate Time-to-Fill, Source-of-Hire reports - Candidate funnel analysis - Exportable to Excel/PDF | Backend, Frontend | MVP

## Technical Stack
Layer | Component | Technology/Tool | Purpose | Task Type | Priority
Frontend | Framework | React / Next.js | Modern UI framework with SSR support | Frontend | MVP
Frontend | UI Library | Tailwind CSS / Material UI | Responsive design and components | UI | MVP
Frontend | State Management | Redux / Context API | Application state management | Frontend | MVP
Frontend | Authentication | JWT + HTTP-only cookies | Secure client-side auth | Frontend | MVP
Backend | API Framework | Python FastAPI / Node.js Express | RESTful API development | Backend | MVP
Backend | Language | Python 3.11+ / Node.js 18+ | Core programming language | Backend | MVP
Backend | API Documentation | Swagger / OpenAPI | Auto-generated API docs | Backend | MVP
Backend | Validation | Pydantic (FastAPI) / Joi (Express) | Request/response validation | Backend | MVP
Database | Primary DB | PostgreSQL 15+ | Structured data storage | Backend | MVP
Database | Search Engine | Elasticsearch 8.x | Full-text and semantic search | Backend | MVP
Database | Caching | Redis | Session and query caching | Backend | Phase II
Database | ORM | SQLAlchemy / Prisma | Database abstraction layer | Backend | MVP
AI/ML | Embedding Model | Sentence-BERT (all-MiniLM-L6-v2) | Semantic similarity calculations | AI/ML | MVP
AI/ML | NLP Library | spaCy / Hugging Face Transformers | Text processing and entity extraction | AI/ML | MVP
AI/ML | ML Framework | PyTorch / scikit-learn | Model training and fine-tuning | AI/ML | Phase II
AI/ML | Resume Parsing | pyresparser / Custom NLP pipeline | Extract structured data from resumes | AI/ML | MVP
AI/ML | Sentiment Analysis | VADER / DistilBERT | Analyze candidate communication tone | AI/ML | MVP
Storage | File Storage | AWS S3 / Azure Blob Storage | Resume and document storage | Backend | MVP
Storage | CDN | CloudFront / Azure CDN | Fast static asset delivery | Backend | MVP
Infrastructure | Cloud Platform | AWS / Azure | Hosting and infrastructure | Backend | MVP
Infrastructure | Container | Docker | Application containerization | Backend | MVP
Infrastructure | Orchestration | ECS Fargate / Kubernetes | Container orchestration | Backend | MVP
Infrastructure | CI/CD | GitHub Actions / GitLab CI | Automated deployment pipeline | Backend | MVP
Infrastructure | Monitoring | Grafana + Prometheus | System metrics and alerting | Backend | MVP
Infrastructure | Logging | CloudWatch / ELK Stack | Application and error logging | Backend | MVP
Security | Authentication | JWT + RBAC | Token-based auth with role permissions | Backend | MVP
Security | Encryption | AES-256 (at rest) + TLS 1.3 (in transit) | Data encryption | Backend | MVP
Security | Secret Management | AWS Secrets Manager / Azure Key Vault | Secure credential storage | Backend | MVP
Security | API Security | Rate limiting + CORS + Input validation | Prevent attacks and abuse | Backend | MVP
Integration | Job Boards | LinkedIn API, Indeed API | Job posting automation | Backend | Phase II
Integration | Calendar | Google Calendar API, Microsoft Graph API | Interview scheduling sync | Backend | Phase II
Integration | Email | SendGrid / AWS SES | Transactional email delivery | Backend | MVP
Integration | Video Conferencing | Zoom API / Microsoft Teams API | Auto-generate meeting links | Backend | Phase II

## Resource Plan
Role | Required Skills | Estimated Effort | Min Cost (INR/Month) | Max Cost (INR/Month) | Total Min Cost (INR) | Total Max Cost (INR) | Priority | Status | Notes
TOTAL ESTIMATED COST |  |  |  |  | ₹ 20,70,000 | ₹ 57,00,000
Full Stack Developer | React, Node.js/Python, PostgreSQL, REST APIs | 6-9 months (Full-time) | 80,000 | 1,50,000 | 4,80,000 | 13,50,000 | Critical - NOW | Hiring | Primary developer for MVP. Senior level: ₹1.2-1.5L, Mid: ₹80K-1L
Backend Developer | Python/Node.js, FastAPI/Express, Database design | 6-9 months (Full-time) | 70,000 | 1,30,000 | 4,20,000 | 11,70,000 | Critical - NOW | Hiring | Focus on API and integrations. Senior: ₹1-1.3L, Mid: ₹70K-90K
ML/AI Engineer | Python, PyTorch, NLP, Sentence-BERT, spaCy | 4-6 months (Part-time initially) | 1,00,000 | 2,00,000 | 4,00,000 | 12,00,000 | High | Needed Soon | Resume parsing and matching algorithms. Specialized role with premium rates
UI/UX Designer | Figma, Wireframing, User research, Prototyping | 2-3 months | 50,000 | 1,00,000 | 1,00,000 | 3,00,000 | High | Needed Soon | Design all interfaces before development. Senior: ₹80K-1L, Mid: ₹50K-70K
DevOps Engineer | AWS/Azure, Docker, CI/CD, Monitoring | 1-2 months (Part-time) | 80,000 | 1,50,000 | 80,000 | 3,00,000 | Medium | Phase II | Infrastructure setup and deployment. Part-time or consultant basis
QA Engineer | Test automation, Selenium, API testing | 2-3 months | 45,000 | 80,000 | 90,000 | 2,40,000 | Medium | Phase II | Quality assurance and testing. Can be junior-mid level
Product Manager | Agile, Roadmap planning, Stakeholder management | Ongoing (Part-time) | 60,000 | 1,20,000 | 3,60,000 | 7,20,000 | Medium | Current | RRG + hired PM. Part-time 6 months estimated
Solution Architect (Consultant) | System design, Architecture patterns, Scalability | 2-4 weeks | 2,00,000 | 3,50,000 | 1,00,000 | 3,50,000 | Critical - NOW | Needed | Expert advice on architecture. Consultant hourly/project basis
Technical Writer | Documentation, User guides, API docs | 1 month | 40,000 | 70,000 | 40,000 | 70,000 | Low | Phase II | Documentation and training materials. Contract basis

## Detailed Cost Breakdown
Cost Category | Item | Quantity/Duration | Unit Cost (INR) | Min Total (INR) | Max Total (INR) | Notes
Human Resources | Full Stack Developer (Senior) | 9 months | 1,50,000/month | 10,80,000 | 13,50,000 | Including benefits and overhead
Human Resources | Full Stack Developer (Mid-level) | 9 months | 80,000/month | 4,80,000 | 7,20,000 | Alternative to senior developer
Human Resources | Backend Developer (Senior) | 9 months | 1,30,000/month | 9,36,000 | 11,70,000 | API and database specialist
Human Resources | Backend Developer (Mid-level) | 9 months | 70,000/month | 4,20,000 | 6,30,000 | Alternative to senior
Human Resources | ML/AI Engineer | 6 months | 1,50,000/month | 4,00,000 | 12,00,000 | Part-time to full-time progression
Human Resources | UI/UX Designer | 3 months | 70,000/month | 1,00,000 | 3,00,000 | Full project design phase
Human Resources | DevOps Engineer (Part-time) | 2 months | 1,00,000/month | 80,000 | 3,00,000 | Infrastructure setup
Human Resources | QA Engineer | 3 months | 60,000/month | 90,000 | 2,40,000 | Testing and quality assurance
Human Resources | Product Manager (Part-time) | 6 months | 80,000/month | 3,60,000 | 7,20,000 | Project coordination
Human Resources | Solution Architect (Consultant) | 1 month | 2,50,000/month | 1,00,000 | 3,50,000 | 2-4 weeks consultation
Human Resources | Technical Writer | 1 month | 55,000/month | 40,000 | 70,000 | Documentation
|  |  | SUBTOTAL - HR | ₹ 20,70,000 | ₹ 57,00,000
Infrastructure | AWS/Azure Hosting (Monthly) | 12 months | 30,000/month | 3,60,000 | 7,20,000 | EC2, RDS, S3, CloudFront
Infrastructure | Domain & SSL Certificates | 1 year | 5,000 | 5,000 | 10,000 | Custom domain and security
Infrastructure | Email Service (SendGrid/SES) | 12 months | 5,000/month | 60,000 | 1,20,000 | Transactional emails
Infrastructure | Monitoring Tools (Grafana Cloud) | 12 months | 10,000/month | 1,20,000 | 1,80,000 | Performance monitoring
Infrastructure | CI/CD Pipeline (GitHub Actions) | 12 months | 3,000/month | 36,000 | 60,000 | Automated deployment
|  |  | SUBTOTAL - Infrastructure | ₹ 5,81,000 | ₹ 10,90,000
Software & Tools | Figma Professional (UI/UX) | 12 months | 1,200/month | 14,400 | 21,600 | Design collaboration
Software & Tools | JetBrains/IDE Licenses | 3 licenses x 12 months | 700/month/user | 25,200 | 42,000 | Development tools
Software & Tools | Jira/Project Management | 12 months | 10,000/month | 1,20,000 | 1,80,000 | Agile project tracking
Software & Tools | Postman Team | 12 months | 5,000/month | 60,000 | 1,00,000 | API testing
Software & Tools | Git Repository (GitHub Teams) | 12 months | 2,000/month | 24,000 | 36,000 | Code repository
|  |  | SUBTOTAL - Software | ₹ 2,43,600 | ₹ 3,79,600
API & Integrations | LinkedIn API (Recruitment) | 12 months | 40,000/month | 4,80,000 | 7,20,000 | Phase II - Job posting & sourcing
API & Integrations | Indeed API Access | 12 months | 20,000/month | 2,40,000 | 3,60,000 | Phase II - Job posting
API & Integrations | Zoom API (Video Interviews) | 12 months | 15,000/month | 1,80,000 | 2,40,000 | Phase II - Interview scheduling
API & Integrations | Google Calendar/Outlook API | One-time setup | 50,000 | 50,000 | 1,00,000 | Calendar integration
|  |  | SUBTOTAL - APIs (Phase II) | ₹ 9,50,000 | ₹ 14,20,000 | Phase II features
Training & Misc | Team Training & Workshops | 5 sessions | 20,000/session | 1,00,000 | 2,00,000 | Skill development
Training & Misc | Documentation & Knowledge Base | One-time | 50,000 | 50,000 | 1,00,000 | Internal wikis and guides
Training & Misc | Legal & Compliance (GDPR/EEOC) | Consultation | 1,00,000 | 1,00,000 | 2,00,000 | Legal review and compliance
Training & Misc | Testing Environments & Data | One-time setup | 50,000 | 50,000 | 1,00,000 | Test data and environments
Training & Misc | Buffer/Contingency (10%) | 10% of HR costs | - | 2,07,000 | 5,70,000 | Unexpected expenses
|  |  | SUBTOTAL - Misc | ₹ 5,07,000 | ₹ 12,70,000
TOTAL MVP COST |  |  |  | ₹ 34,01,600 | ₹ 81,89,600 | Minimum viable product
TOTAL WITH PHASE II |  |  |  | ₹ 43,51,600 | ₹ 96,09,600 | Including Phase II features

## Timeline & Milestones
Phase | Milestone | Duration | Dependencies | Deliverables | Status
Planning | Project Kickoff & Requirements Finalization | Week 1-2 |  | Finalized PRD, WBS, Resource Plan | In Progress
Planning | Technical Architecture Design | Week 2-3 | Milestone 1 | Architecture diagram, Technology stack finalized | Not Started
Planning | UI/UX Design & Wireframing | Week 3-6 | Milestone 2 | Figma designs, User flows, Prototypes | Not Started
Development - Phase 1 | Database Schema & Backend Setup | Week 6-8 | Milestone 3 | PostgreSQL schema, FastAPI skeleton | Not Started
Development - Phase 1 | Authentication & User Management | Week 8-10 | Milestone 4 | Login, Registration, JWT implementation | Partially Done
Development - Phase 1 | Resume Parsing Implementation | Week 10-13 | Milestone 4 | PDF/DOCX parsing, Data extraction | Done
Development - Phase 1 | AI Matching Algorithm (Core) | Week 13-16 | Milestone 6 | Sentence-BERT integration, Match scoring | In Progress
Development - Phase 2 | Job Management Module | Week 16-18 | Milestone 4 | Job CRUD, Job profile management | Not Started
Development - Phase 2 | Candidate Dashboard UI | Week 18-20 | Milestone 5 | Dashboard with application tracking | In Progress
Development - Phase 2 | Recruiter Dashboard & Analytics | Week 20-24 | Milestone 9 | Pipeline view, KPI reports, Charts | Not Started
Development - Phase 2 | Search & Filter Functionality | Week 24-26 | Milestone 7 | Elasticsearch integration, Advanced filters | Not Started
Testing & Deployment | Integration Testing | Week 26-28 | All Dev Milestones | End-to-end test cases, Bug fixes | Not Started
Testing & Deployment | Performance Testing & Optimization | Week 28-29 | Milestone 12 | Load testing, Query optimization | Not Started
Testing & Deployment | UAT (User Acceptance Testing) | Week 29-30 | Milestone 13 | User feedback, Final adjustments | Not Started
Testing & Deployment | Production Deployment | Week 30-31 | Milestone 14 | AWS deployment, Monitoring setup | Not Started
MVP Launch | Internal MVP Launch | Week 32 | Milestone 15 | Live system for Rudra Enterprise recruiters | Not Started
MVP Launch | Post-launch Support & Bug Fixes | Week 32-36 | Milestone 16 | Stabilization, User support | Not Started
Phase II Planning | Client Portal Architecture | Week 36+ | MVP Launch | Multi-tenant design, Client features | Future
Phase II Planning | AI Sourcing & Chatbot Development | Week 36+ | MVP Launch | LinkedIn integration, Chatbot NLP | Future

## Timeline & Milestones1
Phase | Milestone | Duration | Dependencies | Deliverables | Status
Planning | Project Kickoff & Requirements Finalization | Week 1-2 |  | Finalized PRD, WBS, Resource Plan | In Progress
Planning | Technical Architecture Design | Week 2-3 | Milestone 1 | Architecture diagram, Technology stack finalized | Not Started
Planning | UI/UX Design & Wireframing | Week 3-6 | Milestone 2 | Figma designs, User flows, Prototypes | Not Started
Development - Phase 1 | Database Schema & Backend Setup | Week 6-8 | Milestone 3 | PostgreSQL schema, FastAPI skeleton | Not Started
Development - Phase 1 | Authentication & User Management | Week 8-10 | Milestone 4 | Login, Registration, JWT implementation | Partially Done
Development - Phase 1 | Resume Parsing Implementation | Week 10-13 | Milestone 4 | PDF/DOCX parsing, Data extraction | Done
Development - Phase 1 | AI Matching Algorithm (Core) | Week 13-16 | Milestone 6 | Sentence-BERT integration, Match scoring | In Progress
Development - Phase 2 | Job Management Module | Week 16-18 | Milestone 4 | Job CRUD, Job profile management | Not Started
Development - Phase 2 | Candidate Dashboard UI | Week 18-20 | Milestone 5 | Dashboard with application tracking | In Progress
Development - Phase 2 | Recruiter Dashboard & Analytics | Week 20-24 | Milestone 9 | Pipeline view, KPI reports, Charts | Not Started
Development - Phase 2 | Search & Filter Functionality | Week 24-26 | Milestone 7 | Elasticsearch integration, Advanced filters | Not Started
Testing & Deployment | Integration Testing | Week 26-28 | All Dev Milestones | End-to-end test cases, Bug fixes | Not Started
Testing & Deployment | Performance Testing & Optimization | Week 28-29 | Milestone 12 | Load testing, Query optimization | Not Started
Testing & Deployment | UAT (User Acceptance Testing) | Week 29-30 | Milestone 13 | User feedback, Final adjustments | Not Started
Testing & Deployment | Production Deployment | Week 30-31 | Milestone 14 | AWS deployment, Monitoring setup | Not Started
MVP Launch | Internal MVP Launch | Week 32 | Milestone 15 | Live system for Rudra Enterprise recruiters | Not Started
MVP Launch | Post-launch Support & Bug Fixes | Week 32-36 | Milestone 16 | Stabilization, User support | Not Started
Phase II Planning | Client Portal Architecture | Week 36+ | MVP Launch | Multi-tenant design, Client features | Future
Phase II Planning | AI Sourcing & Chatbot Development | Week 36+ | MVP Launch | LinkedIn integration, Chatbot NLP | Future

## References & Competitors
Category | Name | URL | Key Features to Learn From | Notes
AI Recruitment | Talentz.ai | https://talentz.ai | AI-powered candidate matching, Resume parsing, Automated screening | Primary competitor - analyze their UX
ATS Platform | Greenhouse | https://www.greenhouse.com | Pipeline management, Interview scheduling, Analytics dashboard | Industry leader - best practices reference
AI Interview | Xenhire | https://www.xenhire.com | AI video interviews, Sentiment analysis, Auto-scoring | Useful for AI interview features (Phase II)
AI Interview | AI Interview Space | https://aiinterview.space/ | Automated video screening, Question generation | Phase II feature inspiration
Recruiting Software | Skilent (Case Study) | https://brocoders.com/case-studies/skilent-recruiting-software/ | Full recruitment cycle automation, Client portal | Architecture reference
AI Sourcing | HireEZ | https://hireez.com/ | AI-powered candidate sourcing, Boolean search, Passive candidate discovery | Sourcing feature inspiration
Talent Intelligence | Aetius | https://www.aetius.com/ | Talent analytics, Market insights, Predictive hiring | Analytics and reporting ideas
Recruitment Platform | Spottal | https://www.spottal.com/ | End-to-end recruitment, CRM features, Automation | Overall platform design reference
API Integration | LinkedIn Developer | https://developer.linkedin.com/product-catalog | LinkedIn API documentation for job posting and candidate sourcing | Required for Phase II integrations

## Risks & Mitigation
Risk ID | Risk Description | Probability | Impact | Mitigation Strategy | Owner
R01 | AI matching accuracy below expectations | Medium | High | Implement feedback loop, Use pre-trained models, Extensive testing with real data | ML Engineer
R02 | Resume parsing errors for complex formats | High | Medium | Support multiple parsing libraries, Manual review option, Continuous improvement | Backend Dev
R03 | Delayed hiring of key developers | Medium | High | Start hiring immediately, Consider contractors, Engage consultants | PM/RRG
R04 | Scope creep beyond MVP | High | High | Strict MVP definition, Regular scope reviews, Change control process | PM
R05 | Integration challenges with job boards | Medium | Medium | Start with fewer integrations, Use well-documented APIs, Budget extra time | Backend Dev
R06 | Performance issues with large candidate database | Low | High | Database optimization, Elasticsearch indexing, Load testing early | Backend Dev
R07 | Security vulnerabilities | Low | Very High | Security audits, Penetration testing, Follow OWASP guidelines, Regular updates | DevOps/Backend
R08 | User adoption challenges | Medium | High | User training, Intuitive UI/UX, Feedback sessions, Iterative improvements | PM/UX Designer
R09 | Budget overrun | Medium | Medium | Detailed cost tracking, Prioritize MVP features, Avoid premature optimization | PM/RRG
R10 | Technology stack mismatch | Low | High | Thorough architecture review, PoC for critical components, Expert consultation | Solution Architect

## API Endpoints
Endpoint | Method | Description | Request Body | Response | Task Type | Priority
/api/v1/auth/register | POST | User registration | email, password, name, role | user_id, token | Backend | MVP
/api/v1/auth/login | POST | User authentication | email, password | token, user_info | Backend | MVP
/api/v1/auth/logout | POST | Logout user | token | success message | Backend | MVP
/api/v1/candidates/upload | POST | Upload resume and parse | file (PDF/DOCX) | candidate_id, parsed_data | Backend, AI/ML | MVP
/api/v1/candidates | GET | List all candidates | filters, pagination | candidate_list | Backend | MVP
/api/v1/candidates/{id} | GET | Get candidate details | - | candidate_profile | Backend | MVP
/api/v1/candidates/{id} | PUT | Update candidate | updated_fields | success message | Backend | MVP
/api/v1/candidates/{id} | DELETE | Delete candidate | - | success message | Backend | MVP
/api/v1/candidates/search | POST | Search candidates | query, filters | ranked_candidates | Backend, AI/ML | MVP
/api/v1/jobs | POST | Create job | title, skills, experience, description | job_id | Backend | MVP
/api/v1/jobs | GET | List all jobs | filters, pagination | job_list | Backend | MVP
/api/v1/jobs/{id} | GET | Get job details | - | job_info | Backend | MVP
/api/v1/jobs/{id} | PUT | Update job | updated_fields | success message | Backend | MVP
/api/v1/jobs/{id} | DELETE | Delete job | - | success message | Backend | MVP
/api/v1/match/{job_id} | GET | Get ranked candidates for job | - | candidate_list with scores | Backend, AI/ML | MVP
/api/v1/match/score | POST | Calculate match score | candidate_id, job_id | relevance_score, breakdown | AI/ML | MVP
/api/v1/feedback | POST | Submit recruiter feedback | candidate_id, job_id, feedback | success message | Backend | MVP
/api/v1/dashboard/recruiter | GET | Get recruiter dashboard data | - | metrics, charts_data | Backend | MVP
/api/v1/reports/summary | GET | Get KPI summary report | date_range | KPI_data | Backend | MVP
/api/v1/reports/export | POST | Export report | report_type, format | file_url | Backend | MVP
/api/v1/email/send | POST | Send email to candidate | candidate_id, template, data | success message | Backend | Phase II
/api/v1/schedule/availability | GET | Get interviewer availability | interviewer_id, date_range | available_slots | Backend | Phase II
/api/v1/schedule/book | POST | Book interview slot | candidate_id, interviewer_id, slot | meeting_id, calendar_invite | Backend | Phase II

## Pricing Models
Plan | Duration/Type | Features | Price | Target Customer | Notes
Free Trial | 1 Month | - Up to 50 candidates - Basic resume parsing - Manual job posting - Email support | $0 | Trial users, Small agencies | Limited features to test the platform
Basic | Monthly/Annual | - Up to 500 candidates - AI matching (basic) - Resume parsing - 5 active jobs - Dashboard & reports - Email support | $199/month or $1,990/year | Small RPO firms, Startups | 10% discount on annual
Premium | Monthly/Annual | - Up to 5,000 candidates - Advanced AI matching - 50 active jobs - Auto job posting (LinkedIn, Indeed) - Advanced analytics - API access - Priority support | $799/month or $7,990/year | Mid-size agencies, Growing companies | Most popular plan
Enterprise | Custom | - Unlimited candidates - Custom AI fine-tuning - Unlimited jobs - Multi-tenant (client portals) - Dedicated account manager - SLA guarantee - Custom integrations - White-label option | Custom pricing | Large RPO firms, Enterprises | Requires consultation and custom contract
Add-ons | Per feature | - AI Chatbot: $99/month - Interview scheduling: $149/month - LinkedIn sourcing: $299/month - Video interview platform: $199/month | Varies | Any plan tier | Optional features to enhance capabilities